## WSR Simulative Data
Prerequisite
|  | Project Name | Mapped SQA on Additional Information Page | Create Sub Project (TRACK) | Mapped Responsibale Personal to TRACK | Mapped Milestone to Sub Project | Start Date/End Date of Milestone
|  | WSR Custmization Project 1 | Raj Gupta | WSR Custmization Sub Project 1 | Jems | WSR Milestone 1 | 1-March 2024 -31 -March 2024
[6 empty] | WSR Milestone 2 | 1-April 2024 -30 -April 2024
|  |  |  | WSR Custmization Sub Project 2 | Bob | WSR Milestone 3 | 1-Feb 2024 -29 -Feb 2024
[6 empty] | WSR Milestone 4 | 1-March 2024 -31 -March 2024
[6 empty] | WSR Milestone 5 | 1-April 2024 -30 -April 2024
Add WSR | Note :- After click on add button session project getting display as following
|  | Resend |  |  |  |  | Send For Approval | Save | Cancel
| Project Code : | WSECP1 |  | Project Name : | WSR Custmization Project 1 |  | Account Name: | lifeline
| SDLC Model: | Implementation |  | Marlabs Vertical: | Domestic Business
| Week: | Week 01 |  | Track: | WSR Custmization Sub Project 1
Basic Information :
| Sprint / Milestone Name: | WSR Milestone 1
Schedule Variance (ScV)
| Planned Start Date: | 2024-03-01 | Revised Start Date: | 2024-03-01 |  | Schedule Variance (ScV): | 0.16
| Planned End Date: | 2024-03-26 | Revised End Date: | 2024-03-30
| Scope (Till Date) |  |  |  | Effort (Till Date) :
| Overall Scope: | It’s a textaria user can enter comment under the Overall Scope textaria |  |  | Overall Efforts: | It’s a textaria user can enter comment under the Overall Efforts textaria
Unit Of Scope:
| PS: | 3 | SpV: | 0.33333 | PE: | 3 | EV: | 0.33333
| AS: | 4 |  |  | AE: | 4
| Quality Of Deliverables | [5 empty] | Approval Status
| RRD: | 4 |  |  |  |  | Status:
|  |  | TD: | 3 |  |  | Sender's Remark:
| DRD: | 5 |  |  | RE: | 0.73684 | SQA Remark:
|  |  | UAT: | 2 |  |  | PHI Summary:
| CRD: | 5 |  |  |  |  | Approved Date:
| Code Review Method: | A - Automation
SQA Login ( Approval person)
WSR Report Week
Previous Week
| 2024 - Week 1 (01 March 2024 to 08 March 2024) | [8 empty] | Sr. No | Colore Plate | PCI Score
| Track | Milestone | Week | EV | SpV | RE | ScV | Status | More Details
| - | - | - | - | - | - | - | -
WSR Report Week
Cuurent Week
| 2024 - Week 1 (01 March 2024 to 08 March 2024) |  |  |  |  | Approved | Reject
| Project Code: | WSECP1 | Account Name: | lifeline | Project Name: | WSR Custmization Project 1 | SDLC Model: | Implementation
| Marlabs Vertical: | WSR Custmization Sub Project 1
| Track | Milestone | Week | EV | SpV | RE | ScV | Status | More Details
| WSR Custmization Sub Project 1 | WSR Milestone 1 | Week 01 | 0.33333 | 0.33333 | 0.73684 | 0.16 | Approved
| Project Code : | WSECP1 |  | Project Name : | WSR Custmization Project 1 |  | Account Name: | lifeline
| SDLC Model: | Implementation |  | Marlabs Vertical: | Domestic Business
| Week: | Week 01 |  | Track: | WSR Custmization Sub Project 1
Basic Information :
| Sprint / Milestone Name: | WSR Milestone 1
Schedule Variance (ScV)
| Planned Start Date: | 2024-03-01 | Revised Start Date: | 2024-03-01 |  | Schedule Variance (ScV): | 0.2
| Planned End Date: | 2024-03-26 | Revised End Date: | 2024-03-31
| Scope (Till Date) |  |  |  | Effort (Till Date) :
| Overall Scope: | It’s a textaria user can enter comment under the Overall Scope textaria |  |  | Overall Efforts: | It’s a textaria user can enter comment under the Overall Efforts textaria
Unit Of Scope:
| PS: | 50 | SpV: | 1.4 | PE: | 44 | EV: | -0.20455
| AS: | 120 |  |  | AE: | 35
| Quality Of Deliverables | [5 empty] | Approval Status
| RRD: | 30 |  |  |  |  | Status:
|  |  | TD: | 47 |  |  | Sender's Remark:
| DRD: | 44 |  |  | RE: | 0.58889 | SQA Remark:
|  |  | UAT: | 64 |  |  | PHI Summary:
| CRD: | 85 |  |  |  |  | Approved Date:
| Code Review Method: | A - Automation
Note - Close WSR Milestone 1 from Project >> Plan >> WBS and submit another WSR report by selecting WSR Milestone 2 by Responsible persons login, Login As SQA and verify Track which has asscociated with WSR Milestone 2 which has come for approval
SQA Login ( Approval person)
WSR Report Week
Previous Week
2024 - Week 1 (01 March 2024 to 08 March 2024)
| Track | Milestone | Week | EV | SpV | RE | ScV | Status | More Details
| WSR Custmization Sub Project 1 | WSR Milestone 1 | Week 01 | -0.20455 | 1.4 | 0.58889 | 0.2 | Closed
WSR Report Week
Cuurent Week
| 2024 - Week 1 (01 April 2024 to 08 April 2024) |  |  |  |  | Approved | Reject
| Project Code: | WSECP1 | Account Name: | lifeline | Project Name: | WSR Custmization Project 1 | SDLC Model: | Implementation
| Marlabs Vertical: | WSR Custmization Sub Project 1
| Track | Milestone | Week | EV | SpV | RE | ScV | Status | More Details
| WSR Custmization Sub Project 1 | WSR Milestone 2 | Week 05 | -0.11765 | 1.4444 | 0.58423 | 0.52632 | Approved
| Project Code : | WSECP1 |  | Project Name : | WSR Custmization Project 1 |  | Account Name: | lifeline
| SDLC Model: | Implementation |  | Marlabs Vertical: | Domestic Business
| Week: | Week 05 |  | Track: | WSR Custmization Sub Project 1
Basic Information :
| Sprint / Milestone Name: | WSR Milestone 2
Schedule Variance (ScV)
| Planned Start Date: | 2024-04-01 | Revised Start Date: | 2024-04-01 |  | Schedule Variance (ScV): | 0.52632
| Planned End Date: | 2024-04-20 | Revised End Date: | 2024-04-30
| Scope (Till Date) |  |  |  | Effort (Till Date) :
| Overall Scope: | It’s a textaria user can enter comment under the Overall Scope textaria |  |  | Overall Efforts: | It’s a textaria user can enter comment under the Overall Efforts textaria
Unit Of Scope:
| PS: | 45 | SpV: | 1.4444 | PE: | 34 | EV: | -0.11765
| AS: | 110 |  |  | AE: | 30
| Quality Of Deliverables | [5 empty] | Approval Status
| RRD: | 33 |  |  |  |  | Status:
|  |  | TD: | 49 |  |  | Sender's Remark:
| DRD: | 40 |  |  | RE: | 0.58423 | SQA Remark:
|  |  | UAT: | 67 |  |  | PHI Summary:
| CRD: | 90 |  |  |  |  | Approved Date:
| Code Review Method: | A - Automation
Note on E11: User can able to Resend for Approvla WSR Report
Note on K11: User should be able to saved the WSR report details
Note on J133: After Reject the WSR report is again avaialble for update by sender login
After send for approval WSR report should be get display by SQA login
Affter Approved the WSR report Aproved Status, SQA remark and Approved Date should be get display in Approval Status section.
After Reject the WSR report By SQA login RESEND button should be get display by sender Login and, its should be able to update and rend for approval WSR report
Aftre click on More details following display details should be get display by SQA login,
Note - Since none of the milestones have been closed, Previous week's details will show as blank
After Reject the WSR report By SQA login RESEND button should be get display by sender Login and, its should be able to update and rend for approval WSR report
Aftre click on More details following display details should be get display by SQA login,

## Master Data
Note : Hardcoded Values
Sr. NO | Code Review Method:
1 | A - Automation
2 | M - M
3 | A-M – Automation and Munual
4 | NA – Not Applicable